## Instructions
Change Order Log Template with Punch List
Purpose
This workbook keeps one job's change orders and its punch list in one file. Change Orders logs every requested change with its status and approved amount and shows the contract value after each one. Only approved orders move that value; pending orders are totalled separately as exposure. Punch List tracks closeout items by area with an owner, a due date and an overdue flag. Dashboard sums both up. Replace the synthetic sample job with your own and everything recalculates.
Clean-room disclosure
Clean-room disclosure: every formula, layout, instruction and sample figure in this workbook was authored from scratch for Field Service Software IO. No vendor workbook, gated template, branding or sample dataset was downloaded, inspected, mirrored, transformed or adapted in building this file. The project, names, amounts and dates are synthetic and for illustration only.
What’s in this workbook
Change Orders |  | Project name and original contract value at the top, then one row per change order: CO #, date submitted, description, requested by, amount requested (negative for a credit), status, approved amount and date decided. Days open, the running contract value and a Row check are calculated.
Punch List |  | One row per closeout item: item #, area or room, description, trade, responsible person, date added, due date, status and date closed. Days open, an Overdue flag and a Row check are calculated.
Dashboard |  | The as-of date, then the original and revised contract value, approved and pending changes, approval rate, average days to approve, the oldest pending order, punch list counts, Rows to check and Data check.
How to use this workbook
1. If your spreadsheet app opens the file read-only, turn on editing so the formulas calculate.
2. On Change Orders, type your project name in B1 and the original contract value in B2.
3. Clear the sample change orders (columns A to H, rows 5 onward) and add yours. Keep each CO # unique. Pick Requested by and Status from the dropdowns. Type a credit as a negative amount.
4. When an order is approved, set Status to Approved and type the approved amount and the date decided. Rejected and Void orders need a date decided and no approved amount.
5. On Punch List, clear the sample items and add yours. Every item needs an area, description, trade, responsible person, date added, due date and status. A Closed item needs a date closed.
6. On Dashboard, set the as-of date. The sample date is typed in so the sample numbers stay put; type =TODAY() there to use the real date.
7. Fix every Row check that is not OK. Dashboard results read Check data until Data check reads OK.
Colour legend
Colour legend
Input — enter or edit your own data here
Calculated — formula-driven, please do not overwrite
Output — key result for reporting and dashboards
Using this workbook in Google Sheets
Other spreadsheet apps: the file is a plain .xlsx with no macros. To bring it into Google Sheets, choose File > Import > Upload, select this file and choose Insert new sheet(s). Formatting, dropdowns and colors can differ after an import, so check the results before you rely on them.
Limitations
This is a spreadsheet log for one job, not project management software. It does not route approvals, store signed change order forms, track retainage or lien waivers, or schedule work. It gives no contract or legal advice. Change Orders and Punch List formulas, dropdowns and checks reach row 501 (497 change orders and 500 punch items). Days to approve counts calendar days. Dates must fall between 1950 and 2099.
Free template from Field Service Software IO: browse more free field service templates →

## Change Orders
Project | Riverside Medical Office Building, mechanical subcontract
Original contract | 486500 | Only Approved orders move the running contract value. Pending orders are totalled as exposure on Dashboard.
CO # | Date submitted | Description | Requested by | Amount requested | Status | Approved amount | Date decided | Days open | Running contract value | Row check
CO-001 | 2026-08-04 | Add four VAV boxes, level 3 fit-out | Owner | 12400 | Approved | 11800 | 2026-08-19 | 15 | 498300 | OK
CO-002 | 2026-08-21 | Relocate supply duct around new beam | GC | 3850 | Approved | 3850 | 2026-08-28 | 7 | 502150 | OK
CO-003 | 2026-09-09 | Extra crane lift for the rooftop unit | Field | 6200 | Rejected |  | 2026-09-30 | 21 | 502150 | OK
CO-004 | 2026-09-22 | Delete one exhaust fan (credit) | Owner | -4500 | Approved | -4500 | 2026-10-06 | 14 | 497650 | OK
CO-005 | 2026-10-08 | Reroute condensate drains, slab conflict | Field | 9750 | Pending |  |  | 25 | 497650 | OK
CO-006 | 2026-10-27 | Add fire damper at new shaft opening | GC | 2300 | Pending |  |  | 6 | 497650 | OK

## Punch List
Item # | Area or room | Description | Trade | Responsible | Date added | Due date | Status | Date closed | Days open | Overdue | Row check
1 | Level 2 east | Balance VAV-2E-04 to design airflow | Mechanical | Dana | 2026-10-12 | 2026-10-26 | Closed | 2026-10-24 | 12 | No | OK
2 | Level 2 east | Label disconnect for fan coil FC-2E-1 | Electrical | Luis | 2026-10-12 | 2026-10-26 | Open |  | 21 | Yes | OK
3 | Level 2 west | Insulate exposed chilled water valve | Mechanical | Dana | 2026-10-14 | 2026-11-04 | Ready for review |  | 19 | No | OK
4 | Roof | Seal curb flashing at RTU-1 | Mechanical | Marco | 2026-10-15 | 2026-10-29 | Open |  | 18 | Yes | OK
5 | Roof | Point RTU-1 alarms to building system | Controls | Priya | 2026-10-15 | 2026-11-12 | Open |  | 18 | No | OK
6 | Level 1 lobby | Replace cracked diffuser cover | Electrical | Luis | 2026-10-20 | 2026-10-30 | Closed | 2026-10-29 | 9 | No | OK
7 | Level 1 lobby | Adjust vestibule door closer | Mechanical | Marco | 2026-10-22 | 2026-11-05 | Open |  | 11 | No | OK
8 | Mechanical room | Tag backflow preventer with test date | Plumbing | Ana | 2026-10-23 | 2026-10-31 | Closed | 2026-10-31 | 8 | No | OK

## Dashboard
Change Order Log and Punch List
Project | Riverside Medical Office Building, mechanical subcontract
As-of date | 2026-11-02 | Days open, oldest pending and overdue items count to this date. Type =TODAY() to use the real date.
Metric | Result | How it is calculated
Original contract | 486500 | The original contract value typed on Change Orders.
Approved changes | 11150 | Approved amounts on Approved orders; credits are negative.
Revised contract value | 497650 | Original contract plus approved changes.
Change as share of original | 2.292% | Approved changes divided by the original contract; n/a when the original is 0.
Pending change orders | 2 | Orders with status Pending.
Pending value | 12050 | Amount requested on Pending orders: exposure not yet in the contract.
Approval rate | 75% | Approved / (Approved + Rejected); n/a with none decided. Void orders are left out.
Average days to approve | 12 | Average of date decided minus date submitted on Approved orders; n/a with none approved.
Oldest pending (days) | 25 | Days the oldest Pending order has been open at the as-of date; 0 with none pending.
Punch items | 8 | Rows in use on Punch List.
Punch items open | 5 | Items not Closed (Open or Ready for review).
Punch items overdue | 2 | Items not Closed whose due date is before the as-of date.
Punch closed share | 37.5% | Closed items divided by all items; n/a with no items.
Rows to check | 0 | Rows whose Row check is not OK, plus a blank or invalid original contract or as-of date.
Data check | OK | OK when Rows to check is 0. Until then the results above read Check data.
Free template from Field Service Software IO: browse more free field service templates →