## Instructions
Field Service Software Implementation Checklist
Purpose
This workbook tracks the two parts of a field service software switch that decide whether you can go live: getting your data across, and finishing the cutover tasks. The Migration Map lists every data object you are moving, with its source, target, owner, record count and load status. The Go-Live Checklist lists the cutover tasks with owners, due dates and the gate tasks that must be done first. The Dashboard turns both into a readiness score and a go/no-go against your own threshold and gates. Replace the sample rows with your own; everything recalculates.
Clean-room disclosure
Clean-room disclosure: every formula, layout choice, instruction and sample figure in this workbook was written from scratch for Field Service Software IO. No vendor workbook, template, branding or dataset was used. All objects, owners, counts and dates are made up for illustration.
What’s in this workbook
Migration Map |  | One row per data object (customers, locations, equipment, price book and so on): source system and fields, target fields, the transform rule, owner, record count, load status, test load date and whether the counts matched after the load. The sheet works out a progress weight from the status, the weighted records and a Row check.
Go-Live Checklist |  | One row per cutover task: task, phase, owner, due date, status, done date and whether it is a gate task that must be done before cutover. The sheet flags overdue tasks against the Dashboard as-of date and checks each row.
Dashboard |  | Your as-of date, go-live date and readiness threshold, then records to migrate, record-weighted migration progress, checklist completion, overdue, blocked and open gate tasks, days to go-live, overall readiness and the go/no-go against your gates.
How to use this workbook
1. If your spreadsheet app opens the file read-only, turn on editing so the formulas calculate.
2. On Dashboard, set the as-of date (usually today), your planned go-live date and the readiness threshold, a share between 0 and 1. The sample uses 0.9.
3. On Migration Map, list each kind of record you are moving, one row each. Fill in the source, the target, the transform rule, an owner and the record count from the old system. Pick a status as each object moves: Not started, Mapped, Test loaded, Validated, Final loaded. After each load, type the date and pick Yes in Count matched once the record count in the new system matches the old one.
4. On Go-Live Checklist, list the tasks between now and go-live with a phase, owner, due date and status. Mark a task as a gate task (Yes) when you will not cut over until it is done. Type a done date when a task is Done.
5. Fix any Row check that is not OK, then confirm Data check on Dashboard reads OK. Until it does, the Dashboard figures read Check data.
Colour legend
Colour legend
Input — enter or edit your own data here
Calculated — formula-driven, please do not overwrite
Output — key result for reporting and dashboards
Using this workbook in Google Sheets
To try it in Google Sheets, open Google Sheets, choose File > Import > Upload, pick this .xlsx file and choose Insert new sheet(s). Before you replace the sample rows, check that the Dashboard shows the same sample figures as this file.
Limitations
Migration progress is weighted by record count and status only; it does not know how hard each object is to move. Count matched is your own check after each load; the workbook does not compare the systems for you. The go/no-go summarizes your own threshold and gate tasks; it is not a sign-off from anyone else. Phase plans, training plans and a parallel run are not covered here. Formulas and dropdowns reach row 201 on Migration Map and row 301 on Go-Live Checklist.
Free template from Field Service Software IO: browse more free field service templates →

## Migration Map
Data object | Source system and field(s) | Target field(s) | Transform rule | Owner | Records | Status | Test load date | Count matched after load | Progress weight | Weighted records | Row check
Customers | Old system customer list | Customers | Merge duplicates by phone number | Office manager | 1850 | Validated | 2026-10-21 | Yes | 0.75 | 1387.5 | OK
Service sites / locations | Old system service addresses | Locations | One location per service address | Office manager | 2300 | Validated | 2026-10-21 | Yes | 0.75 | 1725 | OK
Equipment at sites | Equipment spreadsheet | Assets | Link each unit to its location | Service manager | 3100 | Test loaded | 2026-10-28 |  | 0.5 | 1550 | OK
Price book items | Accounting item list | Price book | Map item codes to categories | Owner | 640 | Final loaded | 2026-10-14 | Yes | 1 | 640 | OK
Open jobs and work orders | Old system open jobs | Jobs | Open jobs only, no history | Dispatcher | 120 | Mapped |  |  | 0.25 | 30 | OK
Service agreements | Agreement spreadsheet | Agreements | Next visit from last visit date | Service manager | 410 | Test loaded | 2026-10-28 |  | 0.5 | 205 | OK
Technicians and users | Staff list | Users | One login per person | Owner | 14 | Final loaded | 2026-10-14 | Yes | 1 | 14 | OK
Open invoices (A/R) | Accounting A/R report | Invoices | Balance due only | Bookkeeper | 260 | Not started |  |  | 0 | 0 | OK

## Go-Live Checklist
Task | Phase | Owner | Due date | Status | Done date | Gate task | Overdue | Row check
Sign off the field mapping | Prepare | Owner | 2026-10-20 | Done | 2026-10-19 | No | No | OK
Connect accounting integration in a sandbox | Prepare | Bookkeeper | 2026-10-27 | Done | 2026-10-27 | No | No | OK
Train dispatchers on the board | Train | Office manager | 2026-11-06 | In progress |  | No | No | OK
Train technicians on the mobile app | Train | Service manager | 2026-11-13 | Not started |  | No | No | OK
Freeze new customer entry in the old system | Cutover | Office manager | 2026-11-26 | Not started |  | Yes | No | OK
Run final data load and reconcile counts | Cutover | Office manager | 2026-11-27 | Not started |  | Yes | No | OK
Print first-week schedule as a fallback | Go-live day | Dispatcher | 2026-11-30 | Not started |  | No | No | OK
Daily issue review for two weeks | Hypercare | Owner | 2026-12-14 | Not started |  | No | No | OK
Import historical invoices as PDFs | Cutover | Bookkeeper | 2026-11-20 | N/A |  | No | No | OK
Confirm payment processor account | Prepare | Owner | 2026-10-30 | Blocked |  | No | Yes | OK

## Dashboard
Implementation readiness
Settings
As-of date | 2026-11-02 | Usually today. Due dates before it count as overdue.
Go-live date | 2026-11-30 | The day you plan to start running jobs in the new system.
Readiness threshold (0 to 1) | 0.9 | The readiness you want before you go live.
Metric | Result | How it is worked out
Records to migrate | 8694 | Record counts on Migration Map.
Objects final loaded | 2 | Data objects with the status Final loaded.
Migration progress | 63.85% | Weighted records over all records; Status sets each weight.
Checklist tasks (excluding N/A) | 9 | Rows on Go-Live Checklist, not counting tasks marked N/A.
Checklist done | 22.22% | Done tasks over checklist tasks.
Overdue tasks | 1 | Not Done or N/A, with a due date before the as-of date.
Blocked tasks | 1 | Tasks with the status Blocked.
Gate tasks not done | 2 | Tasks you marked as gate tasks that are not Done yet.
Days to go-live | 28 | Go-live date minus the as-of date.
Overall readiness | 43.04% | The average of migration progress and checklist done.
Go / no-go, against your gates | Not yet | Go: threshold met, nothing overdue or blocked, every gate task Done.
Rows to check | 0 | Row checks not OK, plus blank or out-of-range settings.
Data check | OK | OK when Rows to check is 0; until then, figures read Check data.
Free template from Field Service Software IO: browse more free field service templates →